## Sheet1
ID | Story | Estimate(hours) | Priority (1-5) | Sprint When Finished | Completed
1 | Set up DB in docker container | 1 | 1 | 1 | Done
2 | Design DB Schema | 5 | 1 | 1 | Done
3 | Set up SQLAlchemy | 1 | 1 | 1 | Done
4 | Implement database structure and make it accessible | 5 | 1 | 1 | Done
5 | FastAPI install on docker container | 1 | 1 | 1 | Done
6 | Basic get and post request | 3 | 1 | 1 | Done
7 | FastAPI calls to get and set drone data | 3 | 1 | 1 | Done
8 | Backend integration with db | 2 | 2 | 1 | In Progress
9 | MavLink installed and drone control research | 3 | 1 | 1 | Done
10 | MavProxy setup and flight controller emulator | 2 | 1 | 1 | Done
11 | Mavlink standalone script that flies to waypoint in sim | 2 | 1 | 1 | Done
12 | Mavlink integrated with backend | 4 | 1 | 1 | In Progress
13 | React app base created and functioning | 1 | 1 | 1 | Done
14 | Drone select drop down screen #1 | 2 | 1 | 1 | Done
15 | Map api selected and component implemented | 3 | 1 | 1 | Done
16 | Map svg overlay to display position of selected vehicle | 3 | 2 | 1 | In Progress
17 | React app gauges for altitude and velocity | 2 | 1 | 1 | Done
18 | React app "nav ball" for roll, pitch, yaw of vehicle | 2 | 2 | 1 | In Progress
19 | Front end screen 1 integration with backend and db | 2 | 2 | 1 | In Progress
20 | Mavlink test on hardware | 6 | 1 | 1 | In Progress
21 | Front end screen 2 drone list | 1 | 1 | 2
22 | Front end screen 2 Path design component | 8 | 1 | 2
23 | Front end screen 2 save/load paths for selected vehicle | 3 | 1 | 2
24 | Front end screen 2 swarm paths component | 4 | 2 | 2
25 | Backend support for screen 2 implemented | 3 | 2 | 2
26 | Backend integrated with screen 2 | 3 | 2 | 2
27 | Emergency land procedure | 4 | 1 | 2
28 | Teleop control of vehicles | 5 | 1 | 2
29 | Screen 3 connection manager | 6 | 2 | 3
30 | Screen 3 live data streaming component | 8 | 2 | 3
31 | Test swarm planning in simulation | 6 | 2 | 3
32 | Full shakedown in simulation | 10 | 1 | 3
33 | Full shakedown on hardware | 15 | 1 | 3